## Document History
UniQuE
Standard- Metrics - List
(Engagement Name and Id)
(Client)
Document History
Version | Date | Author | Changes
Review And Approval
Company | Role | Name | Date | Signature
Distribution
Company | Name | Number | Media | Action
Storage
Location | Access | Administrator
Company Confidential - Copyright © 2022 Capgemini - All rights reserved
Template Version Number:Group Reference v1.1

## Core Metrics
Metrics | Development | Development – Agile/SAFe model | Re-Engineering | Maintenance : Enhancements | Maintenance : Production Support | Managed Service | Testing | Hardware Development | Mechanical Development
Ontime Delivery (OTD) | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory
First Time Right (FTR) | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory
Schedule Variance (%) (Agile/SAFe : Release Burn-up) | Mandatory | Mandatory | Mandatory | Mandatory | NA | NA | Mandatory | Mandatory | Mandatory
Effort Variance (%)* | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory
Productivity (Agile/SAFe : Velocity) | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory
Defect Density (for all phases including artifacts) | Mandatory | Mandatory | Mandatory | Mandatory | NA | NA | Mandatory | Mandatory | Mandatory
Delivered Defect Rate (External Defect/KSLOC | Mandatory | Mandatory | Mandatory | Mandatory | NA | NA | NA | Mandatory | Mandatory
Defect Removal efficiency (DRE) | Mandatory | Optional | Mandatory | Optional | NA | NA | Optional | Mandatory | Mandatory
Process Compliance Percentage (%) | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory
Test Passed Percentage (Final Round) | Optional | Optional | Optional | Optional | NA | NA | Mandatory | NA | NA
Defects Acceptance Ratio | Optional | Optional | Optional | Optional | NA | NA | Mandatory | Optional | Optional
SLA Adherence (%) | NA | NA | NA | Optional | Mandatory | Mandatory | NA | NA | NA
Bad Fixes (%) | NA | NA | NA | Optional | Mandatory | Mandatory | NA | NA | NA
Content Adherence (Wt.) | NA | Mandatory | NA | NA | NA | NA | NA | NA | NA
Build Pass Ratio (%) | Optional | Mandatory | Optional | Optional | NA | NA | NA | Optional | Optional
Open Defects ( Ticket Completion Rate in Maintenance : Production Support & Managed Service) | Optional | Mandatory | Optional | Optional | Optional | Mandatory | NA | Optional | Optional
Test Case creation productivity (Testing projects Only) | NA | NA | NA | NA | NA | NA | Mandatory | NA | NA
Test Case execution productivity (Testing projects Only) | NA | NA | NA | NA | NA | NA | Mandatory | NA | NA
Cost Of Quality (COQ) | Mandatory | Optional | Mandatory | Mandatory | NA | NA | Optional | Mandatory | Mandatory
CSAT | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory | Mandatory
* Effort Variance is tracked for only FP project in ALTRAN
Note on B7: Size - as applicable to type of project

## Metrics List_ND&FE
Standard Metrics List for ND/FE Projects (Detailed Definition)
Note: | Schedule Variance, Effort Variance and Other Core Metrics (VV, VVF Ratio) are given in Metrics List for ND & FE . Turnaround Ratio is another core metrics that is shown in the metrics list for Maintenance and Support project. For testing project, additional core metrics on defect acceptance ratio is defined on testing projects metrics list sheet.
TL9000 Metrics (NPR, FRT, OFR, OTD, SQ), detailed definitions along with the information about data source and metrics use considerations are provided in separate Metrics Handbook. Refer link for more details: http://home.intra.aricent.com/functions/quality/QMS/QMS-Metrics_Measurement.aspx
# | Metrics Name | Mathematical Definition | Data Source | Data Items | Consideration | Applicability
1 | Productivity* * see details on the 'Details_Productivity Definition' sheet | Size / Effort in person days | Project plan. | Size of the code delivered. | One-person month = 22 person days. | Mandatory
|  |  | Post Mortem report. | Effort. | Size should be taken in SLOC (New+Modified+Deleted lines of code) and effort in person days.
Baselined code KSLOC count tool
2 | Schedule Variance Both as SVa (schedule variance wrt initial baseline / Last Customer Approved Baseline) and SVb (schedule variance wrt latest baseline) | (Actual End Date – Planned End Date)/(Planned End Date – Planned Start Date+1) (in percentage) | Project plan both latest baseline and initial baseline/ Last Customer Approved Baseline Weekly Status Report | Planned Start and end date of each phase/milestone Actual end date of each phase/milestone | Number of days includes all holidays (Saturdays, Sundays & Company holidays). Sum of Schedule Variance of individual phases may not be equal to overall schedule variance of the project. | Mandatory
Schedule Variance wrt initial (SVa) is calculated with respect to initial or first baselined project plan or Last Customer Approved Baseline. Schedule Variance wrt latest (SVb) is calculated with respect to latest baselined project plan. For More details, refer attached document.
3 | Effort Variance : Both as EVa (effort variance wrt initial baseline / Last Customer Approved Baseline) and EVb (effort variance wrt latest baseline) | (Actual number of person days – Planned number of person days)/Planned number of person days (in percentage) | Project plan both latest baseline and initial baseline/ Last Customer Approved Baseline. Weekly Status Report. QCD Report - "approved Vs AEP" effort | Planned number of person days. Team Size Loading factor of each executive. Actual number of days each executive worked. | One-person month = 22 person days. Loading factor needs to be considered. Take actual number of person days from time sheet. | Mandatory
Effort Variance wrt initial (EVa) is calculated with respect to initial or first baselined project plan or Last Customer Approved Baseline. Effort Variance wrt latest (EVb) is calculated with respect to latest baselined project plan
For More details, refer attached document.
4 | Defect Density
4.1 | Artifact Defect Density
4.1.1 | SRS Defect Density | Defects / Size (in terms of no. of requirements) | Defects: Inspection disposition sheet Size: As mentioned in the scope of inspection in inspection template or equivalent source, take no. of requirements as per SRS doc. (or as used while mapping in RTM) | Defects: count of all accepted C+MA+MI inspection defects (no duplicate or rejected defects) Size: For new SRS, count of all requirements For SRS built over existing SRS (like any version after 1.0), count of all the requirements under the scope of inspection (as mentioned in inspection template or equivalent source) | 1. Handling multiple rounds of review of the same artifact to report overall defect density: 1.a. If each review had a non-overlapping scope, overall defect density is calculated by adding defects of each round and size of each round before dividing defects by size. 1.b. If different rounds of review have some overlapping scope, size of over-lapping portion is counted only once while adding up denominator. So it is unique no. of requirements under review scope of all the rounds of review taken together. 1.c. If in case overlapping scope, we are not able to calculated unique requirements under the scope of all the rounds taken together, overall defect density can not be calculated but only estimated. An unbiased estimator of overall defect density will be average of all the rounds of defect densities. If this average is being used to compare against any target, then hypothesis testing (t-test) has to be done to conclude if target is met or not (any other novice way of comparison is invalid) | Mandatory
4.1.2 | Design Doc. / User Doc. & other MS Word Doc. Artifact | Defects / Size (in MS Word Pages with fonts and format as per standard Aricent templates) | Defects: Inspection disposition sheet Size: As mentioned in inspection template or equivalent source | Defects: count of all accepted C+MA+MI inspection defects (no duplicate or rejected defects) Size: For new word doc. artifact (like Design Doc.), count of all the pages of the baselined artifact For any later version or updates (like version after 1.0), count of all the pages under the scope of inspection (as mentioned in inspection template or equivalent source). this scope can also be confirmed from the revision history of the document. | 1. For each type of artifact (like HLD, LLD, ICD), this metrics should be maintained and used separately. 2. Size count in terms of no. of pages is valid for metrics calculation and deriving baselines only if standard format of Aricent template (with font size, header, footer and other formatting) is not violated. For customer specific template, maintain these metrics and their baselines separately. 3. Handling multiple rounds of review of the same artifact to report overall defect density: 3.a. If each review had a non-overlapping scope, overall defect density is calculated by adding defects of each round and size of each round before dividing defects by size. 3.b. If different rounds of review have some overlapping scope, size of over-lapping portion is counted only once while adding up denominator. So it is unique no. of pages under review scope of all the rounds of review taken together. 3.c. If in case overlapping scope, we are not able to calculated unique pages under the scope of all the rounds taken together, overall defect density can not be calculated but only estimated. An unbiased estimator of overall defect density will be average of all the rounds of defect densities. If this average is being used to compare against any target, then hypothesis testing (t-test) has to be done to conclude if target is met or not (any other novice way of comparison is invalid) | Mandatory
4.1.3 | Test Plans | Defects / Size (in terms of no. of test cases) | Defects: Inspection disposition sheet Size: As mentioned in inspection template or equivalent source as per the scope of inspection (check with test plans for number of test cases) | Defects: count of all accepted C+MA+MI inspection defects (no duplicate or rejected defects) Size: For new test plans, count of all the test cases of the baselined version For any later version or updates (like version after 1.0), count of all the test cases under the scope of inspection (as mentioned in inspection template or equivalent source). This scope can also be confirmed from the revision history of the test plans. | 1. For each type of test plans (like UTP, SITP, RTP and ATP), this metrics should be maintained and used separately. 2. Size count in terms of no. of test cases is valid for metrics calculation and deriving baselines only if test case definitions are consistent. uckets should be made considering this factor too. Generally it is consistent phase-wise at program level. 3. Handling multiple rounds of review of the same artifact to report overall defect density: 3.a. If each review had a non-overlapping scope, overall defect density is calculated by adding defects of each round and size of each round before dividing defects by size. 3.b. If different rounds of review have some overlapping scope, size of over-lapping portion is counted only once while adding up denominator. So it is unique no. of test cases under review scope of all the rounds of review taken together. 3.c. If in case overlapping scope, we are not able to calculated unique test cases under the scope of all the rounds taken together, overall defect density can not be calculated but only estimated. An unbiased estimator of overall defect density will be average of all the rounds of defect densities. If this average is being used to compare against any target, then hypothesis testing (t-test) has to be done to conclude if target is met or not (any other novice way of comparison is invalid) | Mandatory
4.2 | Code Defect Density
4.2.1 | Code Review Defect Density | Defects / Code Size in KSLOC | Defects: Inspection disposition sheet Code Size in KSLOC: Code counting tool report | Defects: count of all accepted C+MA+MI inspection defects (no duplicate or rejected defects) Code size in KSLOC: Count of New+Modified+Deleted logical lines of Code in KSLOC under the scope of inspection using script on AW. (This is mentioned in inspection disposition sheet or an equivalent source) | 1. Handling multiple rounds of reviews to report overall defect density: 1.a. If each review had a non-overlapping scope, overall defect density is calculated by adding defects of each round and size of each round before dividing defects by size. 1.b. If different rounds of review have some overlapping scope, size of over-lapping portion is counted only once while adding up denominator. 1.c. If in case overlapping scope, we are not able to calculated unique size under the scope of all the rounds taken together, overall defect density can not be calculated but only estimated. An unbiased estimator of overall defect density will be average of all the rounds of defect densities. If this average is being used to compare against any target, then hypothesis testing (t-test) has to be done to conclude if target is met or not (any other novice way of comparison is invalid) | Mandatory
4.2.2 | Testing Defect Density | Defects / Code Size in KSLOC | Defects: Test report / Defect Management Tool (Jira/ Excel etc.) Code size in KSLOC: Code counting tool report | Defects: Count total accepted Critical, Major, Minor Defects (Duplicate and rejected are not counted) Total size in KSLOC: Count of New+Modified+Deleted logical lines of Code in KSLOC that was under the scope of testing (as per the baseline at the end of the testing) | 1. Regression testing metrics will not follow this definition; in that case, numerator will have all the accepted C+MA+MI defects (new or legacy) and denominator will have new+modified+deleted+re-used logical lines of code in KSLOC. 2. Additional non-standard view of metrics can be created using code size of the before-testing code baseline. If the code churn is high, this metrics should also be reported. in case of very low code churn, both representation will be more or less same. 3. If same code base has been tested during multiple round of testing, for overall defect density, all accepted bugs should be counted from all the rounds (removing duplicate and rejected bugs), but code size should not be double counted (or in other words, if 3 KSLOC has been tested in first round and in second round, some new 0.5 KSLOC added due to rework along with 3 KSLOC of existing code is tested, then total code size tested is 3.5 not 6.5 (3+0.5+3)). For More details, refer attached document. | Mandatory
4.2.3 | Field Reported Defect Density | Defects / Code Size in KSLOC | Defects: As captured in Defect Management Tool (Jira/ Excel etc.) or CRM tools like Seibell Code size in KSLOC: Code counting tool report | Defects: Count total accepted Critical, Major, Minor Defects (irrespective of new or legacy defects; only duplicate and rejected are not counted) Total size in KSLOC: Count of New+Modified+Deleted+Re-used logical lines of Code in KSLOC (of the latest release in the field) | 1. Since the defined metrics in this row is supposed to track overall stability growth over releases so if needed, additional metrics for comparing post release defect density on the same base (as for testing phases) can also be reported separately. In that case, since size will be new+modified+deleted logical lines of code in KSLOC (but no re-used) so legacy defects from numerator should also be removed. | Mandatory
4.3 | Defect Density for Defect Profiling | Total Number of Defects / Size in KSLOC | Defect logs for Documents Jira/ Excel or any other defect management system. Test Report - Analyser Future score card HDC/RFC Test record tool | Total No. of accepted defects (C+MA+MI) Latest code size in KSLOC for both documents as well as Code as denominator | This measure is to be used for Defect Profiling. For Documents as well as code, size is to be taken as KSLOC from latest code size. All size counting considerations given in code defect density shall apply. | Optional
5 | Process compliance Index | Weighted sum of actual compliance score for each process area / Weighted sum of applicable compliance score for each process area | Process compliance sheet Metrics Collection Sheet SQA Review checklist | Weights for each process area Actual score for each audit checklist item Applicable score for each audit checklist item | It can be calculated from Process compliance sheet directly Basis of this can be IQA audit done by QG | Mandatory
6 | VV Ratio (verification & validation ratio: erstwhile 75% rule) VVF Ratio(verification, validation & field defects ratio: erstwhile 95% rule) | VV Ratio : Defects found by the Aricent Development team during post UT and Pre AT / (Defects found by Aricent during post UT and Pre AT + Defects found by ARICENT direct customer or PQT during their AT or PQT | Jira, Excel or any other defect management system Seibel | Total number of defects (Cr+MA+MI) reported during: a. Aricent post UT and Pre AT b. AT / PQT c. First six months of operation in field | Exclude enhancements while counting the number of defects - Defects found by Aricent during post-UT and pre-release/ AT to the customer is X - Defects found by Aricent’s direct customer (for Services) or PQT (for products) during their AT/PQT is Y - Number of Critical, Major and Minor Field defects in the first six months of operation in the field is Z | Mandatory
|  | VVF Ratio : (Defects found by Aricent during post UT and Pre AT + Defects found by ARICENT direct customer or PQT during their AT or PQT) / Total (Defects found by Aricent during post UT and Pre AT + Defects found by ARICENT direct customer or PQT during their AT or PQT + defects from field in first six months of operation) |  |  | . In case of parallel testing at Aricent and customer end at same time (not final delivery) then X is Aricent + customer defects · Any defects raised by customers before the final delivery date (as agreed in contract) is included in X · Defects reported by customer after final product delivery (as agreed in contract) is included in Y · Any defects (post UT and Pre AT) found by Aricent before the final product delivery is included in X · Any defects found by Aricent after the final product delivery is included in Y · For Products VVF ratio (erstwhile 95% rule) computation starts from the date 1st SPR is reported to Aricent (T0)+6 months · For Services VVF ratio (erstwhile 95% rule) computation starts from the date of launch of product in field(T0)+6 months For More details, refer attached document. | Mandatory
7 | DRE(Defect Removal Efficiency) | Total number of Internal defects / (Total number of Internal defects + Total number of External defects)*100 | Defects: Inspection disposition sheet (Review defect) Defect Management Tool (Jira/ Excel etc.) or CRM tools like Seibell | Defects: Count of all accepted C+MA+MI defects (no duplicate or rejected defects) a. Review/Inspection defects b. UT Defects c. Post UT and Pre-AT Defects d. AT /UAT/ PQT e. First six months of operation in field | This metrics shows the efficiency of removing defects by Internal Review and Testing process before shipment of the product to customer Note: Internal Defects are defects found in internal review and testing. External defects are defects found in UAT or any third party testing | Mandatory
8 | DDR (Delivered Defect Rate) | (Total number of External defects*1000)/Total overall actual effort) | Defects: As captured in Defect Management Tool (Jira/ Excel etc.) or CRM tools like Seibell Effort; Project plan both latest baseline / Last Customer Approved Baseline. | Defects: Count total accepted Critical, Major, Minor Defects (irrespective of new or legacy defects; only duplicate and rejected are not counted) | This metric provides an indication on the quality of the deliverables in terms of external defects reported against the effort | Mandatory
9 | Review Effectiveness | Formula: (Number of Review defects / Total number of Review + Testing + External Defects)*100 | Defects: Inspection disposition sheet (Review defect) Defect Management Tool (Jira/ Excel etc.) or CRM tools like Seibell | Defects: Count of all accepted C+MA+MI defects (no duplicate or rejected defects) a. Review/Inspection defects b. UT Defects c. Post UT and Pre-AT Defects d. AT /UAT/ PQT e. First six months of operation in field | This metric indicates the efficiency of the review process followed in terms of defects detected | Optional
10 | Cost of Quality | (Total Effort for Review & Testing +Total Rework Effort) / Total Effort for the Project | Project plan both latest baseline and initial baseline/ Last Customer Approved Baseline. Weekly Status Report. QCD Report - "approved Vs AEP" effort |  | This metric provides an indication on the % of effort & cost incurred towards Detection & failure related activities. | Mandatory
11 | First Time Right (FTR) | Number of deliveries made right first time (zero loops or no rework or no defects) in a particular period of time. | Delivery Feedback Forms, Monthly Project Status Reports | Delivery Feedback Forms with options - Yes or No | Delivery feedback forms to be filled by customer. Incase there is no response from customer, delivery team fills the data as part of Monthly status report and shares with customer and seeks feedback. | Mandatory
12 | On-Time Delivery | Number of deliveries made on time as per schedule in a particular period of time. | Delivery Feedback Forms, Monthly Project Status Reports | Delivery Feedback Forms with options - Yes or No | Delivery feedback forms to be filled by customer. Incase there is no response from customer, delivery team fills the data as part of Monthly status report and shares with customer and seeks feedback. | Mandatory
13 | Code Coverage
13.1 | Line Coverage | [Total lines executed while testing / total lines of code under testing] (in %) | Code Coverage Tool (like Purecoverage, Bull's Eye etc.) | Data item definitions should be referred from the tool help as per the choice of tool because they vary, though not much, but subtly from tool to tool |  | Mandatory
13.2 | Decision Coverage | [Total decision paths tested while testing / total decision paths in the code under testing] (in %) | Code Coverage Tool (like Purecoverage, Bull's Eye etc.) | Data item definitions should be referred from the tool help as per the choice of tool because they vary, though not much, but subtly from tool to tool |  | Mandatory
Note: | Additional Metrics other Std. Metrics List (in case required)
# | Metrics Name | Mathematical Definition | Data Source | Data Items | Consideration | Applicability
1 | Requirement Stability Index | (1 - (Number of Requirements changed / Total number of Requirements)) (In percentage) | Baselined SRS. | Number of requirements as mentioned in the latest SRS. | Care must be taken in numbering the requirements. | Optional
|  |  | Requirement change management sheet | Total number of changes in each requirement. | All the changes in requirements need to be recorded in the requirement change management sheet or re baselined SRS Only approved change need to be considered
|  |  | Metrics Collection Sheet |  | In case of hierarchical level of requirements, count each of the lowest level of requirement separately
2 | Effort Distribution | Actual effort spent in each sub process as percentage of project effort or process | Time Sheet | Actual effort spent for each activity Total effort spent in the project/Process | For both numerator and denominator unit must be same. One-person month = 22 person days. For calculating intermediately, take the actual effort spent till date. | Optional
3 | Size Variance | (Actual size - Estimated size) / Estimated size | Project plan KSLOC count tool Future scorecard | Estimated size. | SLOC has to be reported by running the script “sloc <file names>” in UNIX servers. Blank lines and comment lines should not be included in SLOC. | Optional
|  |  | Size of baselined artifact | Latest actual size. | If estimation is done in terms of function point, either actual size needs to be converted in function point or estimated size in to SLOC.
4 | Defect Distribution | Distribute defects of each phase: | Jira/ Excel or any other defect management system | Each defect classified by: Severity Phase Injected Root Cause | Classify each defect under the standard classification as mentioned in Process documents | Optional
|  | Severity Phase Injected Root Cause | Inspection defect log and summary HDC/RFC Test record tool |  | Map the classification of the defect from defect management system used in the project to the classification provided in the process documents.
5 | Phase-wise Defect Removal Efficiency | Total number of defects found during that phase / (Total number of defects injected in the phase + Defects escaped from previous phases) | Inspection Summary Jira/ Excel or any other defect management system. WSR; Test record tool | Phase wise distribution of defects found during inspection, reviews and testing | Enhance type of defects need not to be considered | Optional
6 | Inspection / Testing Rate | Size of the artifact / Total effort spent in reviews, inspections, or Testing | Inspection Summary Time Sheet Baselined artifact WSR | Total number of defects found during reviews, inspections, or testing Total effort spent in reviews, inspections, or testing. | Enhance type of defect need not to be considered. Total effort includes: Sum of individual effort spent by each reviewer or tester Effort spent in review meetings Total effort spent in testing phase | Optional
7 | Number of test cases per unit size of the code / functions / requirements | Total number of test case / Size of the code, number of functions, or number of requirements | Test Plan | Number of test cases | Code size is generally taken in KSLOC | Optional
|  |  | Baselined SRS Size of baselined code | Size of baselined code Number of requirements | It can be measured with respect to number of functions (for UT) & requirements (For RT and AT)
Number of functions
8 | Defect Finding Rate | Total no. of defects / total effort in person hour | Total No. of Defects and Effort: Inspection records in inspection template | Total No. of Defects: Critical, Major and Minor Inspection Defects Total review effort in person hour | Metrics should be calculated separately for different type of artifact. | Optional
9 | Cyclomatic Complexity | The cyclomatic complexity of a section of source code is the count of the number of linearly independent paths through the source code.(Useful interpretation) Mathematically, the complexity is then defined as: CC = E − N + 2P Where E is the number of edges of the graph, N is the number of nodes of the graph and P is the number of connected components
9.1 | Average Cyclomatic Complexity | Average of CC of all the functions in the file | KLOCKWORK or Other Static Code Analyzer Tools that give CC analysis | Data item definitions should be referred from the tool help as per the choice of tool because they vary, though not much, but subtly from tool to tool. For example, some tools use CC = E-N+P instead of standard definition as E-N+2P | General Guideline: Cyclomatic Complexity (Function Average) CC <6 : simple; CC 6 to 10 : complex; CC >10 : Very complex & risky | Optional
9.2 | Count of Functions Beyond Complexity Limit | Count of functions with CC beyond a defined limit | KLOCKWORK or Other Static Code Analyzer Tools that give CC analysis | Data item definitions should be referred from the tool help as per the choice of tool because they vary, though not much, but subtly from tool to tool. For example, some tools use CC = E-N+P instead of standard definition as E-N+2P | General Guideline: Functions with CC… CC>=25 : Plan for refactoring (evaluate and decide); CC>= 50 Sure & immediate refactoring | Optional
12 | Projected Effort variance | (EAC(Estimated At Completion) effort-Approved Effort)*100/Approved Effort |  |  | Metrics used to track the on going project performance based on earned value | Optional
13 | Projected schedule variance | (Projected End date- Planned end date)*100/(Planned end date- Actual start date+1) |  |  | Metrics used to track the on going project performance based on earned value | Optional
14 | Projected productivity | Size/EAC effort |  |  | Metrics used to track the on going project performance based on earned value | Optional
15 | CPI(Cost Performance Index) | Earned value effort/Actual effort |  |  | Metrics used to track the on going project performance based on earned value. | Optional
16 | SPI (Schedule Performance Index) | Earned value effort/Planned value effort |  |  | Metrics used to track the on going project performance based on earned value. | Optional

## Metrics List_Maintenance Proj.
Standard Metrics List for Maintenance Projects (Detailed Definition)
Note: | TL9000 Metrics (NPR, FRT, OFR, OTD, SQ), detailed definitions along with the information about data source and metrics use considerations are provided in separate Metrics Handbook. Refer link for more details: http://home.intra.aricent.com/functions/quality/QMS/QMS-Metrics_Measurement.aspx
# | Metrics Name | Mathematical Definition | Data Source | Data Items | Consideration | Applicability
1 | Average time taken to close a problem / Query / issue | Sum of number of days taken to close the problems / total number of problems | Jira or any other defect management system | Problem reporting date + SLAs for each category of the problems (For Due Date Calculation) Problem closing date | It can be calculated separately for each category of the problems | Optional
Helpdesk
CAC HI Sheet HDC/RFC system
2 | Turnaround ratio | Number of problems closed with in SLA / total number of Due Problems that are Closed | Jira or any other defect management system | Problem reporting date + SLAs for each category of the problems (For Due Date Calculation) Problem closing date | Closing ration can not be more than 1 | Mandatory
|  |  | Helpdesk |  | It is higher the better
|  |  | CAC HI Sheet HDC/RFC system |  | It can be calculated separately for each category of the problems
Contract mentioning SLAs
3 | SLA Adherence(%) | (Number of problems closed with in SLA / Total number of Problems Due for Closure) in % | Jira, Excel or any other defect management system CAC HDC/RFC system Contract mentioning SLAs | Problem reporting date + SLAs for each category of the problems (For Due Date Calculation) Problem closing date | % Meeting SLA can not be more than 100%. Mathematically it equal to the product of Closing Ratio and Turnaround Ratio expressed in term of %. | Mandatory
4 | Bad fixes (%) | Fixes that got Re-opened / Total no. of Fixes done till date | Jira or any other defect management system CAC HDC/RFC system Contract mentioning SLAs | Fixes re-opened. Total No. of Problems fixed. |  | Mandatory
5 | Other Std. Metrics listed below detailed definitions along with the information about data source and metrics use considerations are provided in 'Metrics List_ND&FE' worksheet. a. Schedule Variance, b. Effort Variance, c. Customer Satisfaction Rating, d. Process Compliance, e. On-Time Delivery (OTD), f. First Time Right (FTR),
Note: | Additional Metrics other Std. Metrics List (in case required)
# | Metrics Name | Mathematical Definition | Data Source | Data Items | Consideration | Applicability
1 | Problems / issues / query Distribution | Distribute Problems / issues / query | Helpdesk | Each Problems / issues / query classified by: | Classify each Problems / issues / query under the standard classification as mentioned in Process documents | Optional
|  | Severity-wise | E mails | Severity
|  | Area wise |  | Area
|  | Root cause-wise |  | Root cause
2 | Closing Ratio | Number of problems closed / No. of Problems Due for Closure | Jira or any other defect management system | Problem reporting date | This is calculated on a particular periodicity Closing ration can not be more than 1 | Optional
|  |  | Helpdesk CAC HDC/RFC system | Number of problems reported in a particular time period Number of problems pending before particular time period | It is higher the better It can be calculated separately for each category of the problems
3 | Reporting Rate | Number of problems reported / number of days | Jira or any other defect management system | Problem reporting date | It can be calculated separately for each category of the problems | Optional
|  |  | Helpdesk | Total number of problems
|  |  | CAC HDC/RFC system Contract mentioning SLAs | Time period for which it need to be calculated
4 | MTBF (Mean Time Between Failure) | No of Days (duration within which problems are reported) / No of Problems | Jira or any other defect management system CAC HDC/RFC system Contract mentioning SLAs | Problems Reported by Customer Time Duration of Maintenance activity. | Instantaneous MTBF can be grossly approximated with the inverse of Reporting Rate. | Optional
5 | MTTR (Mean Time To Repair) | Average Time to Close a Problem | Jira or any other defect management system CAC HDC/RFC system Contract mentioning SLAs | Reporting Date and Closing Date of each of the problems reported. |  | Optional
6 | Average age of the problem | Sum of weights associated with each of the open problem | Jira ,Excel or any other defect management system | Problem reporting date | It need to be calculated for open problems only | Optional
|  |  | Helpdesk CAC HDC/RFC system | Problem closing date Weights associated with respect to age of the problem | Weights are based on time period for which a problem is open Higher the time period, higher the weight
7 | Penalty SLA Adherence | No. of SLA, having Penalties, met target *100/ total No. of SLAs with Penalty | KPIs tracker | Service Level Management | This metric indicates the % of penalty SLA’s met against total Penalty SLAs applicable. | Optional
8 | % of Incentive/Penalties - Cost | (Incentive Received - Penalty amount paid) /Total revenue | KPIs tracker, emails | Service Level Management | Total net incentive or penalty % paid on total revenue | Optional

## Metrics List-Testing Projects
Standard Metrics List For Testing Projects (Detailed Definition)
Note: | TL9000 Metrics (NPR, FRT, OFR, OTD, SQ), detailed definitions along with the information about data source and metrics use considerations are provided in separate Metrics Handbook. Refer link for more details: http://home.intra.aricent.com/functions/quality/QMS/QMS-Metrics_Measurement.aspx
# | Metrics Name | Mathematical Definition | Data Source | Data Items | Consideration | Applicability
1 | Testing Project Productivity
1.1 | Overall Productivity | Total Test case Executed (NF+Reg) / Person Days | Test Case Execution : Test reports Person Days: Timesheet data/MPP/Excel Sheets Effort | Total Test case Executed (NF+Reg): All the test cases that were executed (not just planned) Person Days: Total Person Days consumed from kick-off to end of the testing project | Data for Person Days to be used should have both the cuts: Normalized Effort as well Non-Normalized. If a set of planned test cases has been de-scoped at later stage before execution, both test cases and the corresponding effort should be taken out of the calculation. | Mandatory
1.2 | Test Planning Productivity | Total Test case* (NF+Reg) / Person Days | Test Case* : Test Plan / Test reports Person Days: MPP/Excel Sheets Effort | Total Test case* (NF+Reg): Use total test case planned till the actual test execution data is not available. Once the actual data of execution is available after the phase replace it with the total test case actually executed. Person Days: Total Person Days consumed from kick-off to end of the test planning phase end (before execution) | Data for Person days to be used will come from MPP and will be non-normalized. If a set of planned test cases has been de-scoped at later stage before execution, both test cases and the corresponding effort should be taken out of the calculation. | Mandatory
1.3 | Test Execution Productivity | Total Test case Executed (NF+Reg) / Person Days | Test Case Execution : Test reports Person Days: MPP/Excel Sheets Effort | Total Test case Executed (NF+Reg): All the test cases that were executed (not just planned) Person Days: Total Person Days consumed for test execution and reporting | 1. Data for Person days to be used will come from MPP and will be non-normalized. 2. Scenarios to look for: Automated and Manual test execution productivity should be separately calculated 3. Regression and New feature bucket can also be explored | Mandatory
2 | Defect Detection Efficiency | Total Defects (NF+Reg)/Total Person months | Total Defects (New feature + Regression): Test report / Defect Management Tool (Jira/Bugzilla etc.) Person Months: Timesheet data/MPP Effort | Total Defects (New feature + Regression): Count total accepted Critical, Major, Minor Defects Person Month: Total Person Months consumed from kick-off to end of the testing project | Duplicated and rejected defects are not considered. Data for Person months to be used should have both the cuts: Normalized Effort as well Non-Normalized. | Optional
3 | Defect Removal efficiency | (No.of Defects found internally)*100 / Total No.of(internal + external) Defects found | No.of Defects found internally, No.of external Defects found | It indicates the number of defects leaked after several levels of review and these defects are slipped to the customer. |  | Optional
3 | Defects Acceptance Ratio | Total Accepted Defects /Total Defects Raised | Total Accepted Defects: Test report / Defect Management Tool (Jira/Bugzilla etc.) Total Defects Raised: Test report / Defect Management Tool (Jira/Bugzilla etc.) | Total Accepted Defects: Count total accepted Critical, Major, Minor Defects Total Defects Raised: Count total Critical, Major, Minor Defects raised | Duplicated and rejected defects are not considered. Metrics for New Feature and Regression should be calculated separately If testing project scope includes document verification also, calculate the same metrics separately using same definition (critical, major and minor defects only). | Mandatory
Test Automation Metrics
4 | Percentage Automation (Overall) | 100* Number of Test Cases automated/ Total Number of Test Cases | Number of Test Cases Automated: Automation as per Test Plan at initial stage; Test Report/Test Harness/ Test Automation Tool post scripting (later stages) Total Number of Test Cases: Test Plan/Report | Number of Test Cases Automated: Count of planned test case automation as per Test Plan at initial stage; Count from Test Harness/ Test Automation Tool as scripting is done (Automation Level 2, 3 and 4 are included; refer to the definition of level of automation in the Automation Index metrics) Total Number of Test Cases: Count planned test cases as per test plan till execution is not done; Once execution is done, use actual number of test cases executed | This metrics should be calculated for New Feature and Regression Testing separately | Optional
5 | Scripting productivity
5.1 | Test cases automated Per Person Day of Scripting Effort | Number of Test Cases automated/ Person Days (for automation effort) | Number of Test Cases Automated: Automation as per Test Plan at initial stage; Test Report/Test Harness/ Test Automation Tool post scripting (later stages) Scripting/Automation Effort in Person Days: MPP/Excel Sheet Effort | Number of Test Cases Automated: Count of planned test case automation as per Test Plan at initial stage; Count from Test Harness/ Test Automation Tool as scripting is done. Person Days (for automation effort): Total Person Days consumed for scripting/automation (including review, verification, validation, if any and rework of scripts) | If tracking of effort is possible, metrics should be reported separately for L-2, L-3 and L-4 test cases (where L stands for level of automation as defined in Automation Index metric) | Optional
5.2 | SLOC Per Person Day of Scripting Effort | Number of KSLOC of script/ Person Days (for automation effort) | Number of KSLOC of script: Using standard code size counting tool available on AW Scripting/Automation Effort in Person Days: MPP/Excel Sheet Effort | Number of KSLOC of script: New+Modified+Deleted logical lines of script code as per standard code counting tool on AW. Person Day (for automation effort): Total Person Days consumed for scripting/automation (including review, verification, validation, if any and rework of scripts) | If tracking of effort is possible, metrics should be reported separately for L-2, L-3 and L-4 test cases (where L stands for level of automation as defined in Automation Index metric) | Optional
6 | Script base churn (Regress.) | Modified and Deleted Code Size in KSLOC / Total script size in KSLOC | Modified and Deleted Code Size in KSLOC & Total script size in KSLOC: Using standard code size counting tool available on AW Scripting/Automation Effort in Person | Modified and Deleted Code Size in KSLOC: Take difference of test suite/script base of last release and latest baseline using standard code counting tool available on AW and use only modified and deleted KSLOC Total script size in KSLOC: Count total code size of test suite/script base of last release |  | Optional
7 | Test case/Script design productivity | (No. of Test cases (scripts) designed)/(Total Test case(scripts) design effort in hours) |  | No. of TCs/scripts designed, Total No. of TC/Script design effort in hours | - This metric indicates the productivity of the team in designing the test cases/scripts (Enter TCs for manual, Scripts for Automation and based on project types for Agile) - The effort entered here should include only the effort spent by the team in designing the test cases/scripts | Optional
8 | Test case/Script execution productivity | (No.of Test cases executed)/ (Total Test case executed effort in hours) |  | No.of Test cases/Scripts executed Total Test case/Scripts executed effort in hours | - This metric indicates the productivity of the team in executing the test cases (Enter TCs for manual, Scripts for Automation and based on project types for Agile) - Effort shall include the set up time and execution time. | Optional
9 | Cost Of Quality (COQ) | COQ = (Cost of Detection+Cost of Failure+Cost of Prevention) Cost of Failure :- (Rework effort )*100/ Actual Effort Cost of Detection :- ((Review effort + Audit effort+ External Review effort )) * 100/ Actual Effort Cost of Prevention : - ((Training effort + Process Improvement effort)) * 100/ Actual Effort |  | Cost of Failure :- Rework efforts for the STLC, Total Actual Effort Cost of Detection :- Review effort, Audit effort, External Review effort, Total Actual Effort Cost of Prevention : - Training effort, Process Improvement effort, Actual Effort | 1. Cost of Failure - Gives an indication of how much effort we are spending in rework and helps the PM in doing RCA and taking corrective actions. 2. Cost of Detection -Give an indication of whether sufficient effort is planned and spent for the review. If sufficient time is not spent, there is a chance of errors getting slipped from our review. Also if the detection effort are very high gives an indication of issues in previous phases 3. Cost of Prevention - Gives an indication of whether sufficient time is planned for training needs of the team and improvements | Optional
10 | Other Std. Metrics listed below detailed definitions along with the information about data source and metrics use considerations are provided in 'Metrics List_ND&FE' worksheet. a. Schedule Variance, b. Effort Variance, c. Customer Satisfaction Rating, d. Process Compliance e. On-Time Delivery (OTD), f. First Time Right (FTR),
Note: | Additional Metrics other Std. Metrics List (in case required)
# | Metrics Name | Mathematical Definition | Data Source | Data Items | Consideration | Applicability
1 | Defect Density
1.1 | Defects Per KSLOC (NF) | Total Accepted Defects /Total size in KSLOC of New Feature(s) | Total Accepted Defects: Test report / Defect Management Tool (Jira/Bugzilla etc.) Total size in KSLOC: Code counting tool report | Total Accepted Defects: Count total accepted Critical, Major, Minor Defects Total size in KSLOC: Count of New+Modified+Deleted logical lines of Code in KSLOC | Duplicated and rejected defects are not considered. Additional bucket with total accepted defects definition as Critical, Major, Minor, Enhancement & Cosmetic defects should be calculated and compared with standard metric wherever needed. | Optional
1.2 | Defects Per KSLOC (Regress.) | Total Accepted Defects /Total size in KSLOC for Regression Testing | Total Accepted Defects: Test report / Defect Management Tool (Jira/Bugzilla etc.) Total size in KSLOC: Code counting tool report | Total Accepted Defects: Count total accepted Critical, Major, Minor Defects Total size in KSLOC: Count of total logical lines of Code in KSLOC. Scope of Regression Testing should include testing of complete code base including New Features added as well as Legacy ones. Hence Code size should be the total Logical Lines of Code (New+Modified+Deleted+Reused) | Duplicated and rejected defects are not considered. Additional bucket with total accepted defects definition as Critical, Major, Minor, Enhancement & Cosmetic defects should be calculated and compared with standard metric wherever needed. | Optional
1.3 | Defects Per Req. (NF) | Total Accepted Defects /Total New Requirements to be tested | Total Accepted Defects: Test report / Defect Management Tool (Jira/Bugzilla etc.) Total New requirements: Software Requirements Specification document/PRD/Equivalent reference document for deriving test cases. | Total Accepted Defects: Count total accepted Critical, Major, Minor Defects Total New requirements: Count of all the requirements as listed in the Software Requirements Specification document/PRD/Equivalent reference document for deriving test cases. (as mapped in Requirement Traceability Matrix) | Duplicated and rejected defects are not considered. In case of services project where an equivalent specification document is not available this metrics will become Not Applicable. | Optional
1.4 | Defects Per Req. (Regress.) | Total Accepted Defects /Total Requirements under the scope of regression | Total Accepted Defects: Test report / Defect Management Tool (Jira/Bugzilla etc.) Total requirements under the scope of regression: Software Requirements Specification document/PRD/Equivalent reference document for deriving test cases. | Total Accepted Defects: Count total accepted Critical, Major, Minor Defects Total requirements under the scope of regression: Count of all the requirements as listed in the Software Requirements Specification document/PRD/Equivalent reference document for deriving regression test cases. | Duplicated and rejected defects are not considered. In case of services project where an equivalent specification document is not available this metrics will become Not Applicable. | Optional
1.5 | Defects Per Test Case (NF) | Total Accepted Defects /Total New Feature Test Cases executed | Total Accepted Defects: Test report / Defect Management Tool (Jira/Bugzilla etc.) Total New Feature Test Cases Executed: Test report / Test Management Tool (Test Harness) | Total Accepted Defects: Count total accepted Critical, Major, Minor Defects Total New Feature Test Cases Executed as per the Test report | Duplicated and rejected defects are not considered. | Optional
1.6 | Defects Per Test Case (Regress.) | Total Accepted Defects /Total Regression Test cases | Total Accepted Defects: Test report / Defect Management Tool (Jira/Bugzilla etc.) Total Regression Test Cases Executed: Regression Test report / Test Management Tool (Test Harness) | Total Accepted Defects: Count total accepted Critical, Major, Minor Defects Total Regression Test Cases Executed as per the Regression Test report | Duplicated and rejected defects are not considered. | Optional
2 | Test Coverage
2.1 | Test Cases Per Req. (NF) | Total No. of NF Test Cases* / Total No. of Testable Requirements corresponding to the new features | Total No. of NF Test Cases* : Test Plan / Test reports Total Testbale New requirements: Software Requirements Specification document/PRD/Equivalent reference document for deriving test cases. | Total No. of NF Test Case* : It is total no. of new feature testing test cases. Use total test cases planned till the actual test execution data is not available. Once the actual data of execution is available after the phase replace it with the total test case actually executed. Total Testable New Requirements: Count of all the requirements as listed in the Software Requirements Specification document/PRD/Equivalent reference document for deriving test cases. (as mapped in Requirement Traceability Matrix) | In case of services project where an equivalent specification document is not available this metrics will become Not Applicable. | Optional
2.2 | Test Cases Per Req. (Regress.) | Total No. of Regress. Test Cases* / Total No. of Testable Requirements under the scope of regression | Total No. of Regress. Test Cases* : Test Plan / Test reports Total No. of testable requirements under the scope of regression: Software Requirements Specification document/PRD/Equivalent reference document for deriving test cases. | Total No. of Regress. Test Case* : It is total no. of regression test cases. Use total test cases planned till the actual test execution data is not available. Once the actual data of execution is available after the phase replace it with the total test case actually executed. Total No. of testable requirements under the scope of regression testing: Count of all the requirements as listed in the Software Requirements Specification document/PRD/Equivalent reference document for deriving test cases. (as mapped in Requirement Traceability Matrix) | In case of services project where an equivalent specification document is not available this metrics will become Not Applicable. | Optional
2.3 | Test Cases Per KSLOC (NF) | Total No. of NF Test Cases* /Total size in KSLOC of New Feature(s) | Total No. of NF Test Cases* : Test Plan / Test reports Total size in KSLOC: Code counting tool report | Total No. of NF Test Case* : It is total no. of new feature testing test cases. Use total test cases planned till the actual test execution data is not available. Once the actual data of execution is available after the phase replace it with the total test case actually executed. Total size in KSLOC: Count of New+Modified+Deleted logical lines of Code in KSLOC |  | Optional
2.4 | Test cases Per KSLOC (Regress.) | Total No. of Regress. Test Cases* /Total size in KSLOC under the scope Regression Testing | Total No. of Regress. Test Cases* : Test Plan, Test reports Total size in KSLOC: Code counting tool report | Total No. of Regress. Test Case* : It is total no. of regression test cases. Use total test cases planned till the actual test execution data is not available. Once the actual data of execution is available after the phase replace it with the total test case actually executed. Total size in KSLOC: Count of total logical lines of Code in KSLOC. Scope of Regression Testing should include testing of complete code base including New Features added as well as Legacy ones. Hence Code size should be the total Logical Lines of Code (New+Modified+Deleted+Reused) |  | Optional
3 | Test Case Failure Percentage
3.1 | TC Failure % (cycle wise) | 100 * Total No. of Test Case Failed in nth cycle/ Total No. of Test Case Executed in nth cycle | Cycle-wise Test Execution and Failure Data from Test report / Test Management Tool (Test Harness) | Total No. of Test Case Failed in nth cycle: As per test report, all the failed test cases in a particular cycle ('passed with condition' are not counted as failed test cases). Total No. of Test Case Executed in nth cycle: Figure as per test report for the particular cycle (Invalid test cases, even if run due to some reason, are not counted) | Metrics should be reported separately for New Feature and Regression testing | Optional
3.2 | TC Failure % (Cumulative) | 100 * Total No. of Test Case Failed Till Date / Total No. of Test Case Executed Till Date | Overall Test Execution and Failure Data from Test report / Test Management Tool (Test Harness) | Total No. of Test Case Failed Till Date: As per test report, all the failed test cases till date. This data is reported simply month by month whatever cumulative test cases failure figure comes as per test execution progress. 'Passed with condition' scenarios are not counted as failed test cases. Total No. of Test Case Executed Till Date: As per test report, all the executed test cases till date. This data is reported simply month by month whatever cumulative test cases execution figure comes as per test progress. Invalid test cases, even if run due to some reason, are not counted. | Metrics should be reported separately for New Feature and Regression testing | Optional
4 | Artifact Defect Density | Refer to common metrics list and definition in NDFE Sheet
5 | Artifact Review Rate | Refer to common metrics list and definition in NDFE Sheet
Test Automation Metrics
6 | Automation Variance | 100* [(Actual no. of test cases automated - Planned no. of test cases to be automated)/ Planned no. of test cases to be automated] | Planned number of Test Cases Automated: Automation as per Test Plan or Test Strategy Doc. Or Project Plan Doc. Where this is mentioned. Actual Automation: Test Report/Test Harness/ Test Automation Tool post scripting (later stages) | No further detailing required. | This metrics should be calculated for New Feature and Regression Testing separately | Optional
7 | Automation Index | [(N1*W1)+(N2*W2)+(N3*W3)+(N4*W4)]/(N1+N2+N3+N4) | Number of Test Cases Automated: Automation as per Test Plan at initial stage; Test Report/Test Harness/ Test Automation Tool post scripting (later stages) Level of automation: as documented in the Test Plan/Report | N1, N2, N3 & N4 are number of test cases with level1, 2, 3 & 4 of automation respectively and W1, W2, W3,W4 are their corresponding weights (take W1=0, W2=1, W3=2, W4=3). Level of Automation with definition is as follows: L1 ->Level 1 ( Manual) -> Manual Test Case Execution L2 ->Level 2(Message Automation) -> Test case script without the verdict L3->Level 3(Testcase Automation) -> Test scenario script with the result verdict L4->Level4 (Suite Automation)-> Complete test suite with the result verdict | This metrics should be calculated for New Feature and Regression Testing separately | Optional
8 | Test Automation Coverage | (No. of Test cases automated)*100/ (No.of Test cases) |  | No. of Test cases automated, No.of Test cases Planned for Automation | - For automation projects and for manual projects that takes up automation of regression test cases can use this metric. - Enter the test cases automated and total number of test cases to calculate the automation coverage | Optional
9 | Design Coverage | (No. of TCs or Scripts Designed)*100/ (No. of TCs or Scripts Planned for Design) |  | No. of TCs/Scripts Planned for Design, No. of TCs/Scripts Designed | -This metric gives the Test Design coverage for the project. -Count the number of scripts for automation projects and number of testcases for manual projects. - For Agile projects, based on the sub project type i.e. manual or automation, capture the corresponding coverage inputs | Optional
10 | Execution Coverage | (No. of Test scripts or Test cases executed)*100/ (No. of Test scripts or Test cases Planned) |  | No. of TCs/scripts executed, No.of TCs/scripts Planned for Execution | - Count the number of scripts for automation projects and number of testcases for manual projects. - For Agile projects, based on the sub project type i.e. manual or automation, capture the corresponding coverage inputs | Optional

## Metrics List - SI Project
SI Metrics - Overall | Phase | RCA Triggers
Schedule Variance | All, Overall | Not meeting the org target
Effort Variance | All, Overall | Not meeting the org target
OTD (On-time delivery) | Customer requested date | Not meeting the org target
Requirement Stability Index [% (Added + Modified + Deleted requirements / Total # of Original requirements as per contract)] | Requirement change | Not meeting the defined target
SI Metrics - Configuration & Customization | Phase | RCA Triggers
< 10% deviation of trace-ability to business functions to customization as per Design observed as part of **SI Core Team Review(SI architect, Product SME, Tech Lead) (Different from the conventional Requirement Traceability Matrix) | **Configuration & Customization | •> 10% deviation of trace-ability to business functions after customization
Prototyping observations (no Critical) based on SI Core team review (Optional metrics if prototype has been included as part of the scope of work as per SoW/Contract) | Configuration & Customization | •Critical observations on prototyping/SI Core team review escalations
Configuration and Customization Defect Density (Number of Defects/ total number of functional test cases or total C&C efforts in Person months) | Configuration & Customization | Not meeting the defined target
Minimum of 80% of positive test cases (sunny day scenarios) out of total number test cases mapped to business functions Minimum of 20% of negative test cases (rainy day scenarios) | Functional Testing | RCA on testing defects if exceeds the defined targets on open defects
Interface coding Defect Density Number of defects (excludes COTS defects)/total Modified Line of Code | Interface coding & unit testing | Not meeting the defined target
SIT defect density (excludes defect raised out of the Core COTS functionality or limitations) Defects/ total KSLOC | Onsite SIT | Not meeting the defined target
•No major operations flow mismatches •Customer defined performance Goals | Non-functional Testing (IT Service operations flow as part of non-functional testing) | •If any of the operations flow defined not met as per the requirement document
Test case execution coverage (No. of Test cases executed/Total no. of test cases planned) | Functional and Non-Functional Testing | Not meeting the defined target
SI Metrics -UAT | Phase | RCA Triggers
• C&C Delivered Defect Density =Number of Defects/ total number of functional test cases or total C&C efforts in Person months | UAT | < 5% of CC Defect Density
•Delivered Interface Code Delivered Defect Density = Number of Defects/ Total Modified Line of Code | UAT | < 8% interface code Defect Density
Test Effectiveness - VV ratio (No. of internal Defects during [functional+non functional testing]/No. of internal defects+customer reported defects during AT) | UAT | >75%
SI Metrics - Vendor | Phase | RCA Triggers
Vendor Deliverables - Schedule | Vendor Deliverable Qualification and Acceptance | Agreed Schedule variance on the deliverables expected from vendors goes beyond 5%
Vendor Deliverables - Quality | Vendor Deliverable Qualification and Acceptance | To be supported by processes in which we establish "acceptance" criteria for vendor deliverables. Quantitative assessment against this criteria is indicator of Vendor Delivery Quality
Vendor Requirement Compliance Matrix (% meeting on total number of technical requirements we signed up with vendor | COTS configuration and Customization phases, Pairwise testing and Onsite System Integration Testing | Requirement Compliance Metrics should be submitted by Vendor (Fully/Partially/Non Complaint). These compliances should be tracked periodically to access GAP's and take necessary action pro-actively.
Vendor testing effectiveness [Number of new defects discovered/(No. of defects discovered & fixed by vendor + Number of new defects discovered)] | Onsite System Integration Testing or Pair wise integration testing | <= 10%

## Metrics List - Agile Project
Standard Metrics List for Agile Projects (Detailed Definition)
Note: | TL9000 Metrics (NPR, FRT, OFR, OTD, SQ), detailed definitions along with the information about data source and metrics use considerations are provided in separate Metrics Handbook. Refer link for more details: http://home.intra.aricent.com/functions/quality/QMS/QMS-Metrics_Measurement.aspx
# | Metrics Name | Metrics Definition | Value add | Formula | Consideration | Data Source | Data Items | Frequency | Applicability
1 | Demo Rating | At the completion of an sprint, it's important to show a demonstration of what had been accomplished to stakeholders in order to provide a measure of progress and to elicit feedback. That demo is rated by the stakeholders in numerical scale of 1-10. That rating is referred as Demo Rating. | It helps to know the quality of Potentially Shippable Product Increment. It highlights the product owner satisfaction level with respect to Potentially Shippable Product Increment provided by Aricent | 1-Low and 10-High. | Rating can be done by defining the evaluation criteria of shippable product. Average can be taken, if more than one scrum team. | E mails Tracking Tool | Numerical scale 1-10 | End of each sprint | Mandatory for all type of projects
2 | Testing Defect Density | Number of defects found post UT Pre AT per unit size | Defect Density is used to compare the relative number of defects in various software components. This helps identify candidates for additional inspection or testing or for possible re-engineering or replacement Another use for Defect Density is to compare subsequent releases of a product to track the impact of defect reduction and quality improvement activities. Normalizing by size allows releases of varying size to be compared. Differences between products or product lines can also be compared in this manner. | Defects / Code Size in KSLOC or Story Point | 1. Regression testing metrics will not follow this definition; in that case, numerator will have all the accepted C+MA+MI defects (new or legacy) and denominator will have new+modified+deleted+re-used logical lines of code in KSLOC. 2. Additional non-standard view of metrics can be created using code size of the before-testing code baseline. If the code churn is high, this metrics should also be reported. in case of very low code churn, both representation will be more or less same. 3. If same code base has been tested during multiple round of testing, for overall defect density, all accepted bugs should be counted from all the rounds (removing duplicate and rejected bugs), but code size should not be double counted (or in other words, if 3 KSLOC has been tested in first round and in second round, some new 0.5 KSLOC added due to rework along with 3 KSLOC of existing code is tested, then total code size tested is 3.5 not 6.5 (3+0.5+3)). | Defects: Test report / Defect Management Tool (DETS/Bugzilla/Rally etc.) Code size in KSLOC: Code counting tool report Story Point: Product Backlog/Sprint Backlog | Defects: Count total accepted Critical, Major, Minor Defects (Duplicate and rejected are not counted) Total size in KSLOC: Count of New+Modified+Deleted logical lines of Code in KSLOC that was under the scope of testing (as per the baseline at the end of the testing) Story Point: Count of accepted story points | End of each sprint | Mandatory for ND/FE projects
3 | Defect density | To check and improve (reduce) the number of defects in delivered task/system. |  | Total Defects( Internal + external)/ Size |  |  |  |  | Optional & applicable in All type of projects.
4 | Delivered Defect Density (as per KLOC) | Metrics used to track the delivered defect w.r.t size in KLOC. |  | External Defects/ Actual Size |  |  |  |  | Mandatory for ND/FE projects
5 | Cumulative Open Defect Count | Cumulative open defects in a given instance. | It helps to get the stability and quality of product | Cumulative open defects as per their severity level | Classify each defect under the standard classification as mentioned in Process documents | Defects: Test report / Defect Management Tool (DETS/Bugzilla/Rally etc.) | Severity wise open defects | End of each sprint | Mandatory for ND/FE projects
6 | Velocity | In project management terms, velocity is the amount of work that a team can complete in a specified period of time. | Project’s velocity helps in assessing how much a team can deliver in terms of Story Points. At the time of Release Planning, customers are allowed to choose the same number of user stories equal to the project velocity measured in the previous sprint or the estimated velocity. Even after a few sprint, team will become better at estimating and its velocity should start to stabilize. With a stable velocity, planning releases and iterations becomes much easier. Management is also satisfied as the team is delivering standard size iterations with fewer surprises. | Amount of work accepted (story points )/Time interval | If project has past release then it will be average of story points accepted in sprints (suppose project has 10 sprints in past release then velocity will be "Accepted story points is release/10"). For the cases where relevant velocity figures are not available project manager shall ask estimation team to breakdown 4-5 odd stories into tasks, sub-tasks and then estimate the hours required to do these tasks, sub-tasks. Project manager thus has both story-points corresponding to these 4-5 stories (from planning poker based relative sizing) and effort in person hours. These two values (story points and effort) can be used to calculate velocity (lets suppose, those 4-5 stories correspond to 20 story points and 300 hours, we know velocity per hour can be taken as 0.066 (=20/300) story points per person hour). This is a virtual velocity and effort planning can initially be based on it; but project manager must re-visit release planning after 3 sprints are completed and replace this velocity with actual one. | Product Backlog/Sprint Backlog | Accepted story points per sprint. Time Interval: Last 3 Sprints All Sprints (if past release data available) | At the end of each 3 multipliers sprint. At the end of release completion | Mandatory in All type of projects.
7 | Average Turn Around Time | Average of time elapsed (in days) to complete per user stories. | Waste reduction, process optimization, Enforces systems thinking, increases productivity, helps to take corrective action faster, input for value stream mapping | Average of (User Stories completion date – User Stories picked date) |  | Product Backlog/Sprint Backlog | User stories completion date User stories picked date | End of each sprint | Optional & applicable in All type of projects.
8 | Content Adherence (weighted) | It refers to the percentage of total accepted story points at the end of sprint out of the total committed story points at the start of sprint | Content Adherence identifies the percentage slippage in the committed content of Potentially Shippable Product Increment. Tracking of content helps in better control on the project. Tracking Content Adherence for each iteration helps in taking early corrective action. | (Total story point accepted/Total story point committed)% | Story Points will be counted from sprint backlog | Sprint Backlog | Total story points accepted at the end of the sprint. Total story points committed at the start of the sprint. | End of each sprint | Mandatory in All type of projects.
9 | Code Coverage % | Percentage of code covered during Testing. Line Coverage Decision Coverage | It is used for measuring the sufficiency of test cases executed to test the developed software. | Line Coverage [Total lines executed while testing / total lines of code under testing] (in %) Decision Coverage [Total decision paths tested while testing / total decision paths in the code under testing] (in %) |  | Code Coverage Tool (like Purecoverage, Bull's Eye etc.) | Data item definitions should be referred from the tool help as per the choice of tool because they vary, though not much, but subtly from tool to tool | End of each sprint | Optional & applicable in All type of projects.
10 | RTF (Running Tested Feature) | RTF (Running Tested Feature) is an indicator which shows, how many features in a software is passing all their acceptance test cases, in a given instance. | If the organization decides to measure the progress of the project by demanding continuous delivery of real features, with verified usable test cases, then this single indicator would tell the management all the information required to measure the progress of the project. Whenever a new feature is developed, there is a need to verify and validate the old features using validating acceptance test cases. Further, care should be taken, to ensure that the newly developed feature does not break the functionality of already built and tested features. In such circumstances, there is a need to monitor and track the project progress at regular intervals to avoid any last minute surprises | (Total features in a software is passing all their acceptance test cases /Total features developed in a given instance)% | Feature count will be based on listed in Sprint Backlog | Test reports Product Backlog/Sprint Backlog | Total features in a software is passing all their acceptance test cases Total features developed in a given instance | End of each sprint | Optional & applicable in All type of projects.
11 | Build Pass ratio | It refers to Percentage of Passed Builds out of Total Builds in a sprint. | It helps to find out the cause for build fail and take corrective action to save the effort | (Passed Builds/Total Builds)% |  | Build status E mails Build tracking tool | Pass build count Total build count | End of each sprint | Mandatory in All type of projects.
12 | Done criteria | All agreed checklist points of Definition of Done completed | It helps to ensure each activity planned at User Stories/Sprint/Release has been implemented. | It is Met if all points completed otherwise Not Met |  | Done criteria checklist | Done criteria check point | End of each sprint | Optional & applicable in All type of projects.
13 | Release Burn-up | It is % delta between committed story points and projected story points. Projected story points are calculated considering past velocity of the team and remaining sprints in the release. | It helps the project to predict if the current content(scope) can be met in the committed timelines | {[(Scope in story points) - (Projected story points to be completed by end of release)] / Velocity} % | In the initial Sprints, a Content Adherence of 85-90% need not result in RED RAG status for the project since there are many upcoming iterations and the project has an opportunity to make up. By the same token, during later iterations, a content adherence of 90-95% may need to be highlighted with a RED RAG status as there are lesser opportunities to make up. The formula is depicted with an example in the Burn Up template. | Sprint Burn-up template | Release Scope Projected accepted story points Actual accepted story points Velocity | End of each sprint | Mandatory for all type of projects
14 | Open defect- ageing | Average Time taken to close the open defects ( No of sprints taken to close the open defect) | It helps the project to predict how long the defect is open and will help to create focus if its long overdue | (Avg of Total no of defects open) / (No of sprints its open) |  | Email , tracking tool | No of open defects at the each sprints No of | End of each sprint | Mandatory for all type of projects
15 | Defect Removal efficiency | This metrics shows the efficiency of removing defects by Internal Review and Testing process before shipment of the product to customer | This metric will be helpful to find out the quality of testing and reviews the team is performing. Based on the value of this metric, teams can look at strengthening the testing and review process in case of gaps. 100% indicates that all the defect which are injected in the product is removed via internal testing and reviews, and there is no slippage of defects to other testing teams or to the customer. | total number of Internal defects / (Total number of Internal defects + Total number of External defects)*100 | Internal Defects are defects found in internal review and testing. External defects are defects found in UAT or any third party testing |  |  |  | Mandatory for all type of projects
16 | DDR (Delivered Defect Rate) | This metric provides an indication on the quality of the deliverables in terms of external defects reported against delivery size | This metric provides an indication on the quality of the deliverables in terms of external defects reported against delivery size | (Total number of External defects*1000)/Total overall Size in KSLOC) |  |  |  |  | Mandatory for all type of projects
17 | Cost of Quality | This metric provides an indication on the % of effort & cost incurred towards Detection & failure related activities. | While planning for a Sprint/Release the task planning should be done in such a way that the teams should be able to capture their effort towards creation, review, rework, testing of the user story. | (Total Effort for Review & Testing +Total Rework Effort) / Total Effort for the Project |  |  |  |  | Mandatory for all type of projects
18 | Other Std. Metrics listed below detailed definitions along with the information about data source and metrics use considerations are provided in 'Metrics List_ND&FE' worksheet. a. Schedule Variance, b. Effort Variance, c. VV (verification & validation) and VVF (verification, validation & field defect) Ratio (erstwhile 75% - 95% Rule), d. Customer Satisfaction Rating, e. Process Compliance f. On-Time Delivery (OTD) g. First Time Right (FTR)
Note: | Additional Metrics other Std. Metrics List (in case required)
# | Metrics Name | Metrics Definition | Value add | Formula | Consideration | Data Source | Data Items | Frequency | Applicability
1 | Content Adherence | It refers to the percentage of total accepted user stories at the end of sprint out of the total committed user stories at the start of sprint | Content Adherence identifies the percentage slippage in the committed content of Potentially Shippable Product Increment. Tracking of content helps in better control on the project. Tracking Content Adherence for each iteration helps in taking early corrective action. | (Total user stories accepted/Total user stories committed)% | Only those low level user stories will be counted which is taken in sprint backlog. | Sprint Backlog | Total user stories accepted at the end of the sprint. Total user stories committed at the start of the sprint. | End of each sprint | Mandatory for all type of projects
2 | Agility Index | It shows the percentage of Agility of the ongoing process as per SDMP Agile | Adherence to Agile/Scrum Principle | As per defined checklist points | Each point is applicable | Agility Index sheet | Phase wise agility index Compliance (%) | End of each sprint | Mandatory for all type of projects
3 | Automated test cases % | It is the Number of test cases automated wrt total test cases written | It helps to save the effort and get the confidence on good product quality to check the running tested feature at end of every sprint/release. | 100* Number of Test Cases automated/ Total Number of Test Cases | This metrics should be calculated for New Feature and Regression Testing separately | Number of Test Cases Automated: Automation as per Test Plan at initial stage; Test Report/Test Harness/ Test Automation Tool post scripting (later stages) Total Number of Test Cases: Test Plan/Report | Number of Test Cases Automated: Count of planned test case automation as per Test Plan at initial stage; Count from Test Harness/ Test Automation Tool as scripting is done (Automation Level 2, 3 and 4 are included; refer to the definition of level of automation in the Automation Index metrics) Total Number of Test Cases: Count planned test cases as per test plan till execution is not done; Once execution is done, use actual number of test cases executed | End of each sprint | Optional & applicable in All type of projects.
4 | Test Cases/Size (KLOC or Story Point) | It is the number of test cases made per size | It is used for measuring the sufficiency of test cases to test the developed software. | Number of Test cases/(KLOC or Story Point) |  | Test Plan Product Backlog | Number of Test cases KLOC Story Point | End of each sprint | Optional & applicable in All type of projects.
5 | % Bad Fixed | It refers to percentage of re-opened defect out of fixed defect | It helps to take corrective action for high bad fixes | Fixes that got Re-opened / Total no. of Fixes done till date |  | Defect Management Tool (DETS/Bugzilla/Rally etc.) | Re-opened defects Fixed defects count | End of each sprint | Optional & applicable in All type of projects.
6 | Review Effectiveness | This metric indicates the efficiency of the review process followed in terms of defects detected | This metric will be helpful to find out the quality of reviews performed by the team. Based on the value of this metric, teams can look at strengthening the review process in case of gaps. 100% indicates that all the defect which are injected in the product is removed via internal reviews. | (Number of Review defects / Total number of Review + Testing + External Defects)*100 |  |  |  |  | Mandatory for all type of projects
7 | Productivity (as per KLOC) | This metrics gives an indication on the effort required to complete a work measured in terms of size |  | Formula:( Size)/ (Total Effort) | If UOM (Unit of Measure) is KLOC then Productivity is reflected in LOC/hrs. and defect density as total defects/KLOC. |  |  |  | Optional & applicable in All type of projects.

## Metrics List - SAFe
Standard Metrics List For SAFe Projects (Detailed Definition)
Note: | TL9000 Metrics (NPR, FRT, OFR, OTD, SQ), detailed definitions along with the information about data source and metrics use considerations are provided in separate Metrics Handbook. Refer link for more details: http://home.intra.aricent.com/functions/quality/QMS/QMS-Metrics_Measurement.aspx
# | Metrics Name | Metrics Definition | Impact | Formula | Frequency | Value adds | Applicability
1 | Escaped Defects | Use to identify the number of bugs in a build or release after it enters production / release testing phase | Quality | No. of defects post the PI completion | End of each PI | It helps to know the quality of each PI and improve the testing efficiency based on the root cause and learning. Defects can also be classified based on the severity / priority | Mandatory
2 | Story Lead Time | SLT helps to measure how much time has passed from the moment a user story entered a backlog to the point when it is completed. That includes the time the story was simply sitting in your backlog | Delivery | Avg waiting time for each story | From the first week of the PI | The main aim of SLT is to help teams assess and reduce the speed of a value chain | Optional
3 | Story Cycle Time | It covers only the time a story is in progress, helping to measure and reduce the hours spent on it. Story Cycle Time is always shorter than Story Lead Time and takes up half of a sprint or less. | Delivery | Avg cycle time for each user story | For each iteration/sprint | If a story goes from one phase to another, for example from development to testing, it should count in that time as well. | Optional
4 | Feature Lead Time | Lead time, also known as end-to-end cycle time, for a Feature is the average time from when a Feature is first created to the time it is delivered | Delivery | Feature Lead Time = End Date - Start Date (Lead time can be measured in hours, or days). | From the first week of the PI | The Feature Lead Time is the total of the process times, during which the feature is implemented bringing it closer to being delivered, and the queue times, during which a feature could be waiting in a queue, between the start and end dates. Queues can inadvertently increase the lead time. | Optional
5 | Feature Cycle Time | Cycle time for a Feature is the average time from when an Feature first starts to be worked on to when it is fully tested and ready to be delivered (but not necessarily delivered). | Delivery | Feature Cycle Time = End Date - Start Date (Cycle time can be measured in hours, or days) | For each feature in a iteration/sprint | More frequent releases with business requests moving quickly through the lifecycle, adopting lean practices in order to detect bottlenecks and inefficiencies can provide opportunities for improving the cycle time. Controlling the queue (or batch) size is one lean approach to consider | Optional
6 | Story Throughput | Throughput is the amount of work items delivered in a given period of time (e.g. week, month, quarter) | Delivery | Avg story completion in week/sprint/ month | For each ART team in a PI | Throughput is based on real data of team’s capability to deliver. Throughput variability reflects the impact of factors such as story size, complexity, urgency, and person’s skills | Optional
7 | Feature Progress report | The feature progress report tracks the status of features and enablers during PI execution. It indicates which features are on track or behind at any point in time | Quality and Delivery | Plan Vs Actual Plan – Represents the total number of stories planned. Actual – Represents the number of stories completed | For each ART team in a PI | Facilitates decisions about what changes might be necessary to successfully deliver the PI. Less risk if actual within 15% More risk if actual >15% behind | Optional
8 | First time pass Ratio | First-pass ratio measures the percentage of the product passing all quality requirements without rework. | Quality | No. of test cases passed during the first time execution/ Total no. of test cases executed | End of each iteration | With a high first-pass ratio, costly rework is reduced | Mandatory
9 | Unit/ART Test coverage | Percentage of code covered during Testing (Line Coverage) | Quality | 100* Number of Test Cases automated/ Total Number of Test Cases | End of each iteration | It helps to find out the percentage of covered (executed) code by the tests and try to improve it iteration/PI wise | Mandatory
10 | Automation | All the automatable test cases are automated within PI | Quality and Delivery | No. of test cases automated vs no. of test cases planned for automation | For each ART team in a PI | It helps to save the effort and get the confidence on good product quality to check the running tested feature at end of every iteration/PI | Mandatory
11 | Cumulative Open number of defects | Cumulative open defects in a given instance | Quality | Cumulative open defects as per their severity level | End of each iteration | It helps to get the stability and quality of product | Mandatory
12 | Program Predicatability Measure | The report compares actual business value achieved to planned business value All teams’ PI objectives were assigned a business value from 1 to 10 | Quality and Delivery | % Achievement = Actual Total/Planned Total | End of each PI | It helps to know the quality of Potentially Shippable Product Increment. Planned total does not include uncommitted objectives Actual total includes uncommitted objectives % Achievement = Actual Total/Planned Total A team can achieve greater than 100% (as a result of uncommitted objectives achieved) | Mandatory
13 | Program Performance Metrics | Following metrics helps the ART team to track the program performance metrics at end of each PI | Functionality and Quality | Program Velocity Predictability measure # Features planned # Features accepted # Enablers Features planned # Enablers Features accepted # Stories Planned # Stories Completed | End of each PI for all ART team | Helps to track the iteration health and performace of each PI | Optional
Note: These are possible list of metrics that each team can refer to pick and track the relevant one's as per the project needs

## Metrics List - Managed Services
Standard Metrics List For Managed Service Projects (Detailed Definition)
Note: | TL9000 Metrics (NPR, FRT, OFR, OTD, SQ), detailed definitions along with the information about data source and metrics use considerations are provided in separate Metrics Handbook. Refer link for more details: http://home.intra.aricent.com/functions/quality/QMS/QMS-Metrics_Measurement.aspx
# | Metrics Name | Mathematical Definition | Data Source | Consideration | Process Area | Frequency | Applicability
1 | Tickets Inflow Rate | Total number of Service requests reported in the tool/tracker in a month | Customer Tool Report/ Metrics tracker | Total number of Service requests/tickets recorded in the tool/tracker in a month | Request Fulfillment | Monthly | Mandatory
2 | Tickets Outflow Rate | Total number of Service requests reported in the tool/tracker in a month | Customer Tool Report/ Metrics tracker | Total number of Service requests resolved in the tool/tracker in a month | Request Fulfillment | Monthly | Mandatory
3 | SLA Adherence (%)- Resolution | Total number of tickets/SRs resolved within service level agreement in a month /Total number of tickets/SRs due to be resolved in a month | Customer Tool Report/ Metrics tracker | Percentage of service requests/tickets resolved within service level timelines | Request Fulfillment | Monthly | Mandatory
4 | SLA Adherence (%)- First Response | Total number of tickets/SRs responded first time within service level agreement in a month /Total number of tickets/SRs due to be responded in a month | Customer Tool Report/ Metrics tracker | Percentage of service requests/tickets responded within service level timelines | Request Fulfillment | Monthly | Mandatory
5 | Tickets % Breakup - Severity | %age breakup of total tickets/SRs at each Priority/severity level | Customer Tool Report/ Metrics tracker | Percentage of service requests/tickets per each severity | Request Fulfillment | Monthly | Optional
6 | Tickets % Breakup - Status | Number of SR at each stage (Assigned, WIP, Awaiting User Confirmation, Closed) | Customer Tool Report/ Metrics tracker | Total Number of SR at each stage | Request Fulfillment | Monthly | Optional
7 | Tickets % Breakup - Tier group | %age breakup of total tickets/SRs resolved by each Tier level (L1, L2, L3…) | Customer Tool Report/ Metrics tracker | Percentage of Service Requests resolved at first, second and third tier. | Request Fulfillment | Monthly | Optional
8 | Resolution Quality (Bad fixes) | Number of tickets/Service requests re-opened by Customer / Total number of tickets/Service requests resolved | Customer Tool Report/ Metrics tracker | To track and minimize bad fixed for tickets resolved at T1 and T2 level. | Request Fulfillment | Monthly | Mandatory
9 | Ticket Completion Rate | No. of Tickets delivered for the month / No. of Tickets received for the month | Customer Tool Report/ Metrics tracker | Objective of this metric to find out % of Support tickets Delivered compared to Received in particular month. Recived included backlog from last month | Request Fulfillment | Monthly | Mandatory
10 | Productivity (Ticket Handling/PD) - category wise (App, network, security, etc.) | Tickets Resolved /Day/Person at overall or each Tier Level | Customer Tool Report/ Metrics tracker | Number of tickets handled by the team in a month | Request Fulfillment | Monthly | Mandatory
11 | Open Age (days) | Avg of Open age of tickets | Customer Tool Report/ Metrics tracker | Avg Open Age of tickets | Request Fulfillment | Monthly | Mandatory
12 | Avg TAT | Monthly Avg of each Ticket's (closure date - Ticket open date - hold duration) | Customer Tool Report/ Metrics tracker | Average Turn around Time (all severity level) | Request Fulfillment | Monthly | Mandatory
13 | Avg FRT | Monthly Avg of each Ticket's (First response date/time - Ticket open date/time) | Customer Tool Report/ Metrics tracker | First Response Time (all severity level) | Request Fulfillment | Monthly | Mandatory
14 | CSAT (Service Requests) | Monthly CSAT rating received from customer on tickets handling | Customer Tool Report/ Metrics tracker/Emails | Monthly CSAT rating received from customer on tickets handling | Request Fulfillment | Monthly | Mandatory
15 | % Root Cause Analysis (P1s) | # of RCAs done for Pi tickets/# of P1 tickets | Incident Log | % of Root Cause analysis done for all P1 incidents | Incident Management | Monthly | Mandatory
16 | Incident Inflow Rate | Total number of Incidents recorded in the tool/tracker in a month | Incident Log | Total number of Incidents recorded in the tool/tracker in a month | Incident Management | Monthly | Optional
17 | Event % Breakup - Category | Number of Events identified in each category (informational, Warking, Exception) in a month | Event Report/tracker | Number of events per category | Event management | Monthly | Optional
18 | Event to Incident Conversion | Total number of events converted to Incidents / Total number of events reported | Event Report/tracker | Percentage of events that resulted in incidents | Event management | Monthly | Optional
19 | Incident to problem Conversion | Total number of Incidents converted to Problems/ Total number of incidents reported | Event Report/tracker | Percentage of incidents that resulted in Problems | Problem Management | Monthly | Optional
20 | Availability (%)-Service | % of (Agreed Service Time – Downtime)/Agreed Service Time | CAM Sheet/Customer Tools | Duration of service Uptime | Availability Management | Monthly | Mandatory
21 | Availability (%)- resource | Total number of resources available /Total Number of resources required | CAM Sheet/Customer Tools | Availability of Resources out of total resources required | Availability Management |  | Mandatory
22 | Maintainability - MTRS | Total Downtime (hrs.))/ Num of Service Breaks or interruptions | CAM Sheet/Customer Tools | Mean time to resolve/repair Service | Availability Management | Monthly | Mandatory
23 | Reliability - MTBF | (Available Time (hrs.) – Total Downtime (hrs.))/ Num of Breaks or interruptions | CAM Sheet/Customer Tools | Mean time between failures | Availability Management | Monthly | Mandatory
24 | Resource Utilization - % | Number resources utilized/Total number of resources available | CAM Sheet/Customer Tools | % of Resources (Human, HW./ SW, etc.) utilized in a month | Capacity Management | Monthly | Optional
25 | Capacity Utilization - % | (Billed Capacity(hrs.) - Demand(Hrs.))/Billed Capacity(hrs.) | CAM Sheet/Customer Tools | % variance of demand from the capacity (Human resources effort) | Capacity Management | Monthly | Optional
26 | SLA Coverage | Number of services covered by SLAs | KPIs tracker | Services covered by SLAs | Service Level Management | Monthly | Optional
27 | Overall Wt. SLA performance | Number of SLAs where the agreed targets are fulfilled/Total number of agreed SLAs tracked | KPIs tracker | % of SLAs performing asper targets | Service Level Management | Monthly | Mandatory
28 | Penalty SLA Adherence | No. of SLA, having Penalties, met target *100/ total No. of SLAs with Penalty | KPIs tracker | This metric indicates the % of penalty SLA’s met against total Penalty SLAs applicable. | Service Level Management | Monthly | Optional
29 | % of Incentive/Penalties - Cost | (Incentive Received - Penalty amount paid) /Total revenue | KPIs tracker, emails | Total net incentive or penalty % paid on total revenue | Service Level Management | Monthly | Mandatory
30 | Change Acceptance Rate | Number of accepted RFCs/Total number of RFCs generated | Change Management tracker | Change Acceptance Rate | Change and Evaluation Management | Monthly | Mandatory
31 | Rolled back RFCs | Number of RFCs rolled back | Change Management tracker | Number of RFCs rolled back | Change and Evaluation Management | Monthly | Optional
32 | Change Implementation SLA - Maintenance Window | Number of RFCs implemented within the maintenance window/Total number of RFCs planned to be implemented | Change Management tracker | % changes implemented within the maintenance window | Change and Evaluation Management | Monthly | Mandatory
33 | % Changes delayed | Number of RFCs not implemented by target date/Total number of RFCs planned to be implemented | Change Management tracker | % changes not implemented as per the baselined target date | Change and Evaluation Management | Monthly | Mandatory
34 | # of entries in SKMS |  | Knowledge management tracker | # of entries in SKMS - KEDB | Knowledge Management | Monthly | Optional
35 | Number of Releases | Number of releases rolled out into the productive environment, grouped into Major and Minor Releases | Release plan/report | Number of Releases | Release & Deployment Management | Monthly | Optional
36 | Rolled back Releases | Number of releases which had to be rolled back | Release plan/report | Number of Release Back-outs | Release & Deployment Management | Monthly | Optional
37 | # of Releases Deployment | Number of releases which were deployed successfully | Release plan/report | Number of Release deployed successfully | Release & Deployment Management | Monthly | Optional
38 | Deployment Quality | # of defects reported from field which can be attributed to fault in deployment over a period of 6 months from completion of deployment work | Defect tools | # of defects reported from field which can be attributed to fault in deployment over a period of 6 months from completion of deployment work | Release & Deployment Management | Monthly | Mandatory
39 | # of Transitions | Number of deliverables (documents/trainings/etc.) provided as part of transition | transition plan | Number of Transitions | Transition Planning and Support | Monthly | Mandatory
40 | % of Transition delayed | # of deliverables delayed /total # of transitions due to be delivered in the month | transition plan | Transition Delays | Transition Planning and Support | Monthly | Mandatory
41 | VOC | Customer satisfaction survey rating as conducted by VOC team | VOC reports | Customer satisfaction survey rating as conducted by VOC team | General | Annual/Six months as applicable | Mandatory
42 | Attrition | # of resources resigned in a month/Total Resources Deployed | Monthly | # of resources resigned in a month | General | Monthly | Mandatory
43 | Process Compliance | Monthly Process compliance audit | Process compliance sheet | Monthly Process compliance audit | General | Monthly | Mandatory
44 | Project Success Prediction | Monthly Project Success Prediction Score | PSP Sheet | Monthly Project Success Prediction Score | General | Monthly | Mandatory
45 | Program Review Compliance | Monthly Compliance on conducting program reviews | Program Review status/invites | Monthly Compliance on conducting program reviews | General | Monthly | Mandatory
46 | First Time Right (FTR) | Number of deliveries made right first time (zero loops or no rework or no defects) in a particular period of time. | Customer Tool Report/ Metrics tracker |  | Request Fulfillment | Monthly | Mandatory
47 | On-Time Delivery | Number of deliveries made on time as per schedule in a particular period of time. | Customer Tool Report/ Metrics tracker |  | Request Fulfillment | Monthly | Mandatory

## Metrics Used on Need Basis
Additional Metrics other Std. Metrics List (Detailed Definition)
# | Metrics Name | Mathematical Definition | Data Source | Data Items | Consideration
1 | Risk Exposure | Sum total of risk exposure of each identified risk | Risk Management Plan | Probability of each risk | It should be tracked on a defined periodicity
Impact of each risk
2 | Average Customer Satisfaction rating | Total of Overall customer Satisfaction rating / Total number of projects | Customer satisfaction survey reports | Overall customer satisfaction rating | There are multiple survey questionnaire for products and services kind of projects
Total number of projects
3 | Impact of Requirement changes on schedule / effort / size | Change in schedule, effort, or size / First baselined schedule, effort, or size | Requirement change management sheet | Change in Effort, date, or size | Calculate variance as per the definition given for schedule, effort and size variance metrics
|  |  | Metrics Collection Sheet iPLAN - Planner, Future Score card | First baselined effort, schedule, or size | For multiple changes in requirements, these variance may not be additive
4 | Cost of Quality | (Cost of Prevention + Cost of Appraisal + cost of failure) / Total effort of project | Time Sheet iPLAN- Planner Future score card | Effort spent on various activities as mentioned in remarks | Cost of Prevention includes the effort spent on Classroom Training Imparted, Discussions/Brainstorming, Inspections & Reviews – Code, Inspections & Reviews – Design, Inspections & Reviews – Others, Inspections & Reviews - Project Plan, Inspections & Reviews – Requirements, and Inspections & Reviews - Technical Proposals, Inspections & Reviews - Test Plans, Prototyping, Training, Received/Self Learning.
Cost of Appraisal includes the effort spent on Test Automation, Test Execution, Testing - Acceptance Testing, Testing - Release Test, Testing - SI Testing, Testing - SSI Testing, Testing - Unit Testing
Cost of failure includes the effort spent on Defect Management/Re-work
5 | Time to baseline a project plan | Date of first baseline – Date of kick off meeting | Metrics Collection Sheet | Date of first baseline | If value is high, we need to have plan for making a plan
|  |  | Minutes of Kick off Meeting Revision history of Project Plan iPLAN - Planner | Date of kick off meeting | Average value of this metrics at the organization level indicates the overall time taken to prepare a formal project plan
6 | Number of meeting conducted with respect to planned number of meetings | Total number of actual meetings conducted / Total number of planned meetings (in percentage) | Project Plan iPLAN - Planner | Total number of actual meetings conducted | This metric should be calculated for at least following meetings:
|  |  | Records of meetings | Total number of planned meetings | Program Reviews (Mandatory)
Status meetings
Customer meetings
SEPG meetings, etc.
7 | Number of functions or Size of code per requirement | Number of functions or Size of code / total number of requirement | Baselined code | Number of functions | In case functions are not the unit of measure, it can be number of screens, objects, or classes
|  |  | Baselined SRS | Size of code
Total number of requirements
8 | Number of test cases modified / added | Number of test case added or modified after first baseline / Total number of test cases in first baselined test plan (in percentage) | Baselined Test plans | Number of test case added or modified after first baseline | New test cases may be added because of new feature, regression, or unforeseen during first version
Total number of test cases in first baselined test plan
9 | Average effort to close a defect | Total effort spent in closing all defects / Number of defects | Time Sheet | Effort spent for each defect | Exclude enhancements while counting the number of defects and total effort
|  |  | DETS Lite or any other defect management system | Number of defects
10 | Number of defects because of rework | Total number of defects, which are caused by bad fix, patch or rework / Total number of defects found | DETS Lite or any other defect management system | Number of defects because of bad fix, patch or rework | This need to be found for each phase of testing
|  |  | Root cause analysis report | Total number of defects | Defects because of bad fix or rework can be found in subsequent phases also
11 | Average Number of Configurable Items | Total Number of configurable items (documents & code files separately) of each project / Total number of projects | Master list of documents | Number of configurable items of each project. | Only baselined configurable items present in the CM database need to be considered.
|  |  | Configuration management tool. | Total number of projects. | Number of configurable items need to be mentioned in the CM plan
Project database.
12 | Average size of Configurable Item (CI) | Total size of each configurable item (documents & code files separately) / Total number of Configurable Items | Master list of documents | Size of each CI | Document size should be taken in number of pages
|  |  | Configuration management tool | Total number of CIs | Code size should be taken in SLOC
13 | Risk Identification Efficiency | Number of risks occurred which were identified in the project plan / Total number of risks occurred | Risk Management plan | Number of risks occurred which were identified in the project plan
|  |  | Post-mortem report | Total number of risks occurred.
14 | NC age in each stage | Time taken for each NC to move from one stage to another stage | NC tracking tool | Dates for each stage of NC | There are 6 stages from NC to be raised to NC is closed
15 | Time taken to close a NC | Total time to close all NCs / Total number of NCs | NC tracking tool | Date on which NC is raised | Time taken in closing NC in calendar days.
|  |  |  | Date on which NC is closed | For each NC time need to be measured from date of raising a NC to closure of NC in the follow up audit.
The unit of metric is days per NC
16 | NC per Project | Total number of NCs reported in a audit / Total number of projects audited | Audit plan | Number of NCs for each project
|  |  | Audit Report | Number of projects/areas audited
17 | Observations per project | Total number of Observations reported in a audit / Total number of projects audited | Audit plan | Number of Observations for each project
|  |  | Audit Report | Number of projects/areas audited
18 | NC distribution area wise | Number of NCs for each area as percentage of total NCs | Audit plan | Classified area for each NC | Each NC is generally classified as project planning, Quality records, review, etc.
|  |  | Audit Report | Total number of NCs
19 | NC distribution group wise | Number of NCs for each group as percentage of total NCs | Audit plan | Name of group each audited project belong to
|  |  | Audit Report | Total number of NCs
20 | Coverage of Projects in Audit | Number of project audited in each cycle of audit / Total number of open projects in project database (in percentage) | Audit Plan | Number of project audited
|  |  | Metrics Collection Sheet | Total number of open projects in project database

## Details_Productivity Definition
DEFINITIONS OF PRODUCTIVITY:
Overall Productivity (For ND & FE Projects):
Total numbers of lines of code (SLOC: New+ Modified+ Deleted) / Total (Development + Testing) Life Cycle Effort in Person Days
Note: Wherever we use term "total life cycle effort", it includes project management, configuration management and training efforts also.
Code Productivity (For ND & FE Projects):
Total numbers of lines of code (SLOC: New+ Modified+ Deleted) / Total Coding Effort in Person Days
Note: Since we know that many ND & FE projects exclude some phases selectively depending upon the scope of the work; and so overall
productivity may be comparable with in a program but not across the programs because of the variation in the life cycle phases. Hence we
require code productivity that will be a handy measure there to compare across the programs.
POINTS OF CLARIFICATION:
How to calculate overall productivity for …
1. Project where newly written code alone (Development), physical or logical lines?
Logical lines of code to be taken for LOC calculation.
2. Projects where base code is available and project team has to enhance the code by adding some features and across the base code
adding, modifying and deleting the code and test, release the full code. (Project team has to write the test cases, fix the bug even in the
reused code during IT / RT phase)?
Enhancement projects - Count only Add + delete+ modified lines of code and take the overall effort for that enhancement release.
Assumptions:
* If the base code is developed by Aricent and regression test suite is available to run and hence minimal effort is spent for testing. Hence no
change in counting method required.
* Even if the base code is customer code, no change in counting method. Only thing to remember is to compare projects as such not across
the programs and use productivity figure derived from program level baseline for estimation.
3. Project uses auto generated code along with developed code, test the entire code and release (Project team has to write the test cases
, fix the bug even in the reused code during IT / RT phase)?
Tool / Auto generated code should not be taken while computing LOC. If there is any significant modification / update in the tool generated code
, then the modified SLOC (add+ delete+ modify) alone taken in to overall LOC computation.
4. Project used reused code (some std. plug in code, open source, base product code or any other code), integrated, test the entire
code and release?
Stub code should not be included as part of KSLOC calculation. The effort required for writing the stubs is to be mentioned separately in the
estimation sheet and it is part of overall development effort.
Note: If some std. plug in code, open source, base product code or any other code used, still use only modified SLOC (add+ delete+ modify)
alone in to overall LOC computation.
5. Projects where migrated from one environment to another (porting work) ?
The productivity computation for Porting, Customization project is not to be mixed with normal ND & FE projects. We may initially exclude these
projects from reporting till we have significant data to form a separate bucket and facilitate meaningful interpretation of the metrics for such projects.
6. Projects that use multiple languages(C & Java or any combination)?
New, modified, and deleted lines for all languages are added together while computation because even if we segregate line of code, we can not
segregate effort so we have to live with such variations and where such variations affect productivity drastically, let RCA come as the same.
Note: For the purpose of future refernece, if we are able to segregate effort data for the development related to each language, then we should
parallely capture language wise productivity.
Any other special scenario where SQA or Project Manager has reasons to calculate productivity differently, it should be first discussed
and approved by the Quality Group (metrics sub-group) and those scenarios should be handled as exception rather than process.

## Compatibility Report
tan | Compatibility Report for Worksheet in C Users bgh54575 Desktop New folder Final Report Gaps Incorporation Migrated A2 Metrics_Handbook.docx
Run on 3/19/2020 14:04
If the workbook is saved in an earlier file format or opened in an earlier version of Microsoft Excel, the listed features will not be available.
| Minor loss of fidelity | # of occurrences | Version
| An embedded object in this worksheet can't be edited because it was created in a newer version of Microsoft Office. | 4 | Excel 97-2003
| Some cells or styles in this workbook contain formatting that is not supported by the selected file format. These formats will be converted to the closest format available. | 134 | Excel 97-2003